# Vogentout Corporate Website — Phase 01

Stack: Laravel + Admin Panel

## 1) Overview & Key Assumptions

Objective. Launch an SEO‑friendly corporate website that positions Vogentout as an expert in reliability engineering, customised machinery design, and premium engineering components supply.

Phase 01 Scope. Marketing/information website + admin panel for page/content/SEO management, contact/enquiry handling, testimonials. (Quotations & e‑commerce are future phases.)

Timeline Basis. Strict 28 business days from Project Start (Mon, 01 Sep 2025).

## 2) Critical Governance (must‑follow)

- Single Source of Truth. This plan governs scope, dates, and approvals for Phase 01.

- Clock‑Pause Rule. The 28‑BD clock pauses when required inputs are late (content, approvals, assets, payments). The schedule shifts 1:1 by the days delayed.

- Feedback SLA. Each approval/review has 24 hours (minor) or 48 hours (major). No response = silent approval and the project proceeds.

- Content Freeze. Day‑9, 12:00 noon: all Phase 01 content due. Missing items will use professional placeholders and become post‑launch change requests.

- Revision Limits. Each stage includes 1 consolidated round of changes (≤10 comments/page). Extra rounds = change request with time/cost impact.

- Code Freeze. Two business days before the launch window. Only P0 bug fixes are allowed.

- Scope Control. Any net‑new feature/structure change after sign‑off triggers a formal change request.

- Security & Compliance. CSRF, server‑side validation, HTTPS/HSTS & security headers, reCAPTCHA v3, brute‑force throttling, secure password policy for the single admin account.

## 3) Deliverables by Stage (what you get)

- Discovery & SEO Foundation. Competitor scan, keyword map, sitemap, content matrix, measurable success KPIs.

- Wireframes. Mobile‑first UX for key templates (Home, About, Services/Solutions, Components/Products catalogue, Certifications, Testimonials, Contact).

- Laravel Build. Admin (pages, services/solutions, components, testimonials, site settings), SEO fields per page (title, meta, OG, canonical), schema.org, XML sitemap & robots.txt, contact form with mailer.

- QA/Perf/Accessibility. Cross‑browser/device testing,

- Launch Kit. Deployment pipeline, backups, error monitoring, analytics (GA4), and a 5‑business‑day post‑launch bug‑fix window (see Section 11).

## 4) Client Inputs (what we need & when)

Due by Day‑9 (12:00 noon):

- Final logo (vector), brand palette/typography (if any)

- Product & service list; certifications (PDF/JPG)

- 5–10 testimonials (if available)

- Company profile text (About, Vision/Mission, Leadership)

- Contact details

- Imagery library (or stock usage approval)

- Top 10–15 target keywords and 3–5 direct competitors (If not provided, we will decide and proceed.)

Approvals Required:

- Sitemap & SEO brief (end of Day‑5)

- Wireframes (end of Day‑8)

- UI (end of Day‑12)

- Staging site (Day‑25)

## 5) 28 Business Day Timeline (Project Start = Mon, 01 Sep 2025)

Relative plan below + absolute date mapping.

| Day(s) | Calendar Dates | Phase | Team Activities | Client Actions | Outputs |
| --- | --- | --- | --- | --- | --- |
| 1–2 | Sep 01–02 (Mon–Tue) | Kickoff & Discovery | Success criteria, audience/jobs‑to‑be‑done, analytics goals, competitor scan | Share brand files & prior decks | Discovery brief + KPIs |
| 3–5 | Sep 03–05 (Wed–Fri) | SEO & IA | Keyword map, sitemap, content matrix | 24–48h approval SLA | Approved sitemap & SEO brief (Gate‑A) |
| 6–8 | Sep 08–10 (Mon–Wed) | Wireframes | Mobile‑first wires for key templates | Consolidated feedback (1 round) | Approved wires (Gate‑B) |
| 9 | Sep 11 (Thu) | Content Freeze | Prepare UI; lock received content | Deliver remaining content by 12:00 | Content lock list |
| 9–12 | Sep 11–16 (Thu–Tue) | UI Design | Style tile; Home + inner templates | 1 round consolidated feedback | Approved UI (Gate‑C) |
| 13–17 | Sep 17–23 (Wed–Tue) | Build Sprint 1 | Laravel setup; admin; page/SEO models; media library; site settings | — | Working CMS & core models |
| 18–20 | Sep 24–26 (Wed–Fri) | Build Sprint 2 | Frontend templates; contact form; mailer + DB logs; reCAPTCHA; schema; sitemap/robots | Test contact email receipt | Feature‑complete staging |
| 21–22 | Sep 29–30 (Mon–Tue) | Content Entry & On‑page SEO | Enter final copy, alts, internal links; redirects plan | Spot‑check content | All pages populated |
| 23–24 | Oct 01–02 (Wed–Thu) | QA & Hardening | Cross‑browser/device QA; perf tuning; security hardening | UAT prep | QA report & fixes |
| 25 | Oct 03 (Fri) | UAT & Code Freeze | Staging handover; freeze by EOD (P0 fixes only) | UAT sign‑off (Gate‑D) | Go‑live checklist ready |
| 26 | Oct 06 (Mon) | Pre‑Launch | Backups; error monitoring; analytics goals; DNS window confirm | Confirm launch window | Launch runbook |
| 27–28 | Oct 07–08 (Tue–Wed) | Launch & Hypercare | Go‑live; smoke tests; rollback plan on standby | Final accept | Live site + hypercare |

If an earlier launch is required, reduce scope or move the Project Start earlier. Scope‑change requests will adjust time/cost.

## 6) Acceptance Criteria (extract)

- All sitemap pages exist, are responsive, and editable in admin.

- Forms validate, store to DB, and email designated recipients; spam is mitigated.

- No P0/P1 defects outstanding at launch (P2+ scheduled post‑launch).

- Security checks passed (CSRF, auth, rate limiting, headers, env secrets; secure single‑admin access).

## 7) Risks & Mitigations

- R1: Late Content/Approvals. Mitigation: Clock‑Pause rule; single approver.

- R2: Scope Creep. Mitigation: Signed sitemap/wires/UI; change‑request process only.

- R3: SEO Quality. Mitigation: Early keyword map; on‑page checklist.

- R4: Launch Dependencies (DNS, email). Mitigation: Pre‑launch checklist; schedule DNS window 48h prior.

- R5: Stakeholder Churn. Mitigation: One decision‑maker; written decisions recorded.

## 8) Post‑Launch (5 business days)

- Bug‑fix window: P0/P1 defects introduced in Phase 01.

- Analytics & SEO quick wins: Verify goals/events, submit sitemap, review Search Console.

- Training: 60‑minute admin training.

## 9) What We Need Confirmed to Start

- Project Start date (confirmed as Mon, 01 Sep 2025).

- Single approver + escalation contact.

- Hosting/DNS details (or confirmation to host with us).

- Any mandatory compliance (brand/legal) constraints.

Prepared for: Vogentout (Phase 01)
Prepared by: Trendzhub — Web & Product Team